## Slide 1: Process
Statistics

## Slide 2: List of task planned for this sprint
OQ-13 Create sql database
OQ-25 Learning used technologies
OQ-19 Add login/logout functionality
OQ-14 Create and connect BitBucket repository
OQ-15 Populate Database
OQ-16 Create UI for customer requesting a ticket
OQ-17 Function to add the customer to the database after he requested a ticket
OQ-18 Show the ticket to the customer
OQ-20 UI for the officer to signal that he is free
OQ-21 Function to update the database to signal that an officer is free
OQ-22 Function to reset the queue every morning
OQ-23 Function to count how many other customers have requested a ticket of the same type
OQ-24 On the home page, show which counter is serving which customer

## Slide 3: Macro Statistics
All stories were done
All points were done
Number of hours planned = 35,75
Number of hours spent = 41,25

## Slide 4: Task hours
Chart: 
| OQ-13 | OQ-25 | OQ-19 | OQ-14 | OQ-15 | OQ-16 | OQ-17 | OQ-18 | OQ-20 | OQ-21 | OQ-22 | OQ-23 | OQ-24
Hours estimated | 2 | 8 | 4 | 0.25 | 1 | 3 | 5.5 | 2 | 3.5 | 1.5 | 0.5 | 2 | 2.5
Hours spent | 2.25 | 11.5 | 4.5 | 0.16667 | 0.5 | 3.5 | 6.5 | 1.8333 | 5.75 | 1 | 0.33333 | 1.25 | 2.1667

## Slide 5: Detailed statistics
Estimated case
Avarage of hours per task = 2,75
Standard deviation of hours per task = 2,14
Actual case
Avarage of hours per task = 3,17
Standard deviation of hours per task = 3,23

## Slide 6: Detailed Statistics
Story1 | Number of tasks | Points | Total hours estimated | Total hours spent | Error ratio
OQ-10 As a customer, I want to receive a ticket, so that I can satisfy my request | 5 | 3 | 14,35 | 16,55 | 0,87
OQ-5 As an officer, I want to tell the system when I am ready, so that I can serve the next customer | 4 | 1 | 11,6 | 14,05 | 0,83
OQ-8 As an officer, I want to see the queue reset every morning, so that I can start working | 1 | 1 | 2,1 | 2,63 | 0,8
OQ-3 As a customer, I want to know how many other customers are ahead of me, so that I can decide whether to take the ticket or not | 1 | 3 | 3,6 | 3,55 | 1,01
OQ-6 As a customer, I want to see on the display board when it is my time to be served, so that I can go to the counter | 1 | 2 | 4,1 | 4,47 | 0,92

## Slide 7: Detailed Statistics
Total hours estimated = 35,75
Total hours spent = 41,25
Total task estimation error ratio = 0,87