## Foglio1
Story points | Stories | Tasks | Estimated Hours | Hours | estimated minutes | minutes
|  | OQ-13 Create sql database | 2h | 2h 15m
|  | OQ-25 Learning used technologies | 6h | 11h 30m
|  | OQ-19 Add login/logout functionality | 4h | 4h 30m
|  | OQ-14 Create and connect BitBucket repository | 15m | 10m
|  | OQ-15 Populate Database | 1h | 30m
3 | OQ-10 As a customer, I want to receive a ticket, so that i can satisfy my request
|  | OQ-16 Create UI for customer requesting a ticket | 2h 30m | 3h 30m
|  | OQ-17 Function to add the customer to the database after he requested a ticket | 4h | 6h 30m
|  | OQ-18 Show the ticket to the customer | 2h | 1h 50m
1 | OQ-5 As an officer, i want to tell the system when i am ready, so that i can serve the next customer
|  | OQ-20 UI for the officer to signal that he is free | 3h 30m | 5h 45m
|  | OQ-21 Function to update the database to signal that an officer is free |  | 1h
1 | OQ-8 As an officer, i want to see the queue reset every morning, so that i can start working
|  | OQ-22 Function to reset the queue every morning |  | 20m
3 | OQ-3 As a customer, i want to know how many other customers are ahead of me, so that i can decide whether to take the ticket or not
|  | OQ-23 Function to count how many other customers have requested a ticket of the same type |  | 1h 15m
2 | OQ-6 As a customer, i want to see on the display board when it is my time to be served, so that i can go to the counter
|  | OQ-24 On the home page, show which counter is serving which customer |  | 2h 10m