## Slide 1: SPRINT RETROSPECTIVE
Team 11

## Slide 2: Process

## Slide 3: List of task planned for this sprint
OQ-13 Create sql database
OQ-25 Learning used technologies
OQ-19 Add login/logout functionality
OQ-14 Create and connect BitBucket repository
OQ-15 Populate Database
OQ-16 Create UI for customer requesting a ticket
OQ-17 Function to add the customer to the database after he requested a ticket
OQ-18 Show the ticket to the customer
OQ-20 UI for the officer to signal that he is free
OQ-21 Function to update the database to signal that an officer is free
OQ-22 Function to reset the queue every morning
OQ-23 Function to count how many other customers have requested a ticket of the same type
OQ-24 On the home page, show which counter is serving which customer

## Slide 4: Macro statistics
All stories were done
All points were done
Number of hours planned = 35,75
Number of hours spent = 41,25

## Slide 5: Task hours
Chart: 
| OQ-13 | OQ-25 | OQ-19 | OQ-14 | OQ-15 | OQ-16 | OQ-17 | OQ-18 | OQ-20 | OQ-21 | OQ-22 | OQ-23 | OQ-24
Hours estimated | 2 | 8 | 4 | 0.25 | 1 | 3 | 5.5 | 2 | 3.5 | 1.5 | 0.5 | 2 | 2.5
Hours spent | 2.25 | 11.5 | 4.5 | 0.16667 | 0.5 | 3.5 | 6.5 | 1.8333 | 5.75 | 1 | 0.33333 | 1.25 | 2.1667

## Slide 6: Detailed statistics
Estimated case
Avarage of hours per task = 2,75
Standard deviation of hours per task = 2,14
Actual case
Avarage of hours per task = 3,17
Standard deviation of hours per task = 3,23

## Slide 7: Detailed statistics
Story1 | Number of tasks | Points | Total hours estimated | Total hours spent | Error ratio
OQ-10 As a customer, I want to receive a ticket, so that I can satisfy my request | 5 | 3 | 14,35 | 16,55 | 0,87
OQ-5 As an officer, I want to tell the system when I am ready, so that I can serve the next customer | 4 | 1 | 11,6 | 14,05 | 0,83
OQ-8 As an officer, I want to see the queue reset every morning, so that I can start working | 1 | 1 | 2,1 | 2,63 | 0,8
OQ-3 As a customer, I want to know how many other customers are ahead of me, so that I can decide whether to take the ticket or not | 1 | 3 | 3,6 | 3,55 | 1,01
OQ-6 As a customer, I want to see on the display board when it is my time to be served, so that I can go to the counter | 1 | 2 | 4,1 | 4,47 | 0,92

## Slide 8: Detailed statistics
Total hours estimated = 35,75
Total hours spent = 41,25
Total task estimation error ratio = 0,87

## Slide 9: Quality

## Slide 10: Quality
 | Estimated hours | Hours
Unit test | 4 | 2
System test | 4 | 1
Code review | 6 | 3

## Slide 11: Quality
Total estimated time: 14h
Nr of automated unit tests: 0
Only manual tests
Difficulty in meeting the estimates
Due to the lack of knowledge about automated tests methodology

## Slide 12: Assessment

## Slide 13: Current Sprint
Underestimation of tests and learing
Positive 📈
  how to divide work in a big project
Negative 📉
  conceptual schema definition of db
  few effort in unit testing
Notes: le cose che abbiamo sottostimato maggiormente in termini di tempo sono stati i test e il tempo per imparare/ampliare nuove tecnologie/tools
nonostante fosse la prima esperienza di lavoro in team e in un progetto relativamente ampio, siamo stati in grado di suddividerci bene i compiti ognuno secondo le proprie competeze
avremmo dovuto dedicare più tempo alla progettazione del database che poi è stato oggetto di continue modifiche in corso d’opera
poco effort in unit testing perché non avevamo considerato il tempo per eseguirli nei task che li riguardavano; di conseguenza abbiamo inserito troppi task nello sprint

## Slide 14: Future Sprints
Automated Unit Tests
More accurate work log
(More time in DB definition)
Notes: PER GLI SPRINT FUTURI
In fase di planning dare più importanza / considerare di più il tempo necessario allo svolgimento dei test nei task principali. Come? Usando dei software per il testing automatico delle unit (ad es. Junit).
Dovremmo prestare più attenzione a loggare correttamente il nostro effort /tempo impiegato nello svolgimento dei task al fine di avere una più accurata rappresentazione della nostra produttività come team e di conseguenza calibrare meglio il carico di lavoro (nr. di task) nei successivi sprint. Se sappiamo le nostre capacità , possiamo pianificare meglio.
se si progetta meglio il db si evita di perdere tempo in fase di realizzione… come migliorare? semplicemente dedicarci più tempo all’inizio di ogni nuovo progetto

## Slide 15: Efficient Fast Indipendet
Notes: SIAMO ORGOGLIOSI DI:
efficienti come team anche se non rodato
in poco tempo un prodotto semplice ma funzionante
lavorato in modo indipendente back and front –end
….ANCHE SE SONO TRE COSE E NON UNA ;)