## Foglio1
Story points | Stories | Tasks | Estimated Time | Actual Time | E hours | E minutes | E conversion hours | hours | minutes | conversion hours
All Stories
|  | OQ-13 Create sql database | 2h | 2h 15m | 2 | 0 | 2 | 2 | 15 | 2.25
|  | OQ-25 Learning used technologies | 8h | 11h 30m | 8 | 0 | 8 | 11 | 30 | 11.5
|  | OQ-19 Add login/logout functionality | 4h | 4h 30m | 4 | 0 | 4 | 4 | 30 | 4.5
|  | OQ-14 Create and connect BitBucket repository | 15m | 10m | 0 | 15 | 0.25 | 0 | 10 | 0.16667
|  | OQ-15 Populate Database | 1h | 30m | 1 | 0 | 1 | 0 | 30 | 0.5
3 | OQ-10 As a customer, I want to receive a ticket, so that i can satisfy my request | [5 empty] | 0 |  |  | 0
|  | OQ-16 Create UI for customer requesting a ticket | 3h | 3h 30m | 3 | 0 | 3 | 3 | 30 | 3.5
|  | OQ-17 Function to add the customer to the database after he requested a ticket | 5h 30m | 6h 30m | 5 | 30 | 5.5 | 6 | 30 | 6.5
|  | OQ-18 Show the ticket to the customer | 2h | 1h 50m | 2 | 0 | 2 | 1 | 50 | 1.8333
1 | OQ-5 As an officer, i want to tell the system when i am ready, so that i can serve the next customer | [5 empty] | 0 |  |  | 0
|  | OQ-20 UI for the officer to signal that he is free | 3h 30m | 5h 45m | 3 | 30 | 3.5 | 5 | 45 | 5.75
|  | OQ-21 Function to update the database to signal that an officer is free | 1h 30m | 1h | 1 | 30 | 1.5 | 1 | 0 | 1
1 | OQ-8 As an officer, i want to see the queue reset every morning, so that i can start working | [5 empty] | 0 |  |  | 0
|  | OQ-22 Function to reset the queue every morning | 30m | 20m | 0 | 30 | 0.5 | 0 | 20 | 0.33333
3 | OQ-3 As a customer, i want to know how many other customers are ahead of me, so that i can decide whether to take the ticket or not | [5 empty] | 0 |  |  | 0
|  | OQ-23 Function to count how many other customers have requested a ticket of the same type | 2h | 1h 15m | 2 | 0 | 2 | 1 | 15 | 1.25
2 | OQ-6 As a customer, i want to see on the display board when it is my time to be served, so that i can go to the counter | [5 empty] | 0 |  |  | 0
|  | OQ-24 On the home page, show which counter is serving which customer | 2h 30m | 2h 10m | 2 | 30 | 2.5 | 2 | 10 | 2.1667

## tabellaFinale
Story points | Stories | Tasks | Estimated Time | Actual Time | Estimated time converted in hours | Actual time converted in hours
All Stories
|  | OQ-13 Create sql database | 2h | 2h 15m | 2 | 2.25
|  | OQ-25 Learning used technologies | 8h | 11h 30m | 8 | 11.5
|  | OQ-19 Add login/logout functionality | 4h | 4h 30m | 4 | 4.5
|  | OQ-14 Create and connect BitBucket repository | 15m | 10m | 0.25 | 0.16667
|  | OQ-15 Populate Database | 1h | 30m | 1 | 0.5
3 | OQ-10 As a customer, I want to receive a ticket, so that i can satisfy my request
|  | OQ-16 Create UI for customer requesting a ticket | 3h | 3h 30m | 3 | 3.5
|  | OQ-17 Function to add the customer to the database after he requested a ticket | 5h 30m | 6h 30m | 5.5 | 6.5
|  | OQ-18 Show the ticket to the customer | 2h | 1h 50m | 2 | 1.8333
1 | OQ-5 As an officer, i want to tell the system when i am ready, so that i can serve the next customer
|  | OQ-20 UI for the officer to signal that he is free | 3h 30m | 5h 45m | 3.5 | 5.75
|  | OQ-21 Function to update the database to signal that an officer is free | 1h 30m | 1h | 1.5 | 1
1 | OQ-8 As an officer, i want to see the queue reset every morning, so that i can start working
|  | OQ-22 Function to reset the queue every morning | 30m | 20m | 0.5 | 0.33333
3 | OQ-3 As a customer, i want to know how many other customers are ahead of me, so that i can decide whether to take the ticket or not
|  | OQ-23 Function to count how many other customers have requested a ticket of the same type | 2h | 1h 15m | 2 | 1.25
2 | OQ-6 As a customer, i want to see on the display board when it is my time to be served, so that i can go to the counter
|  | OQ-24 On the home page, show which counter is serving which customer | 2h 30m | 2h 10m | 2.5 | 2.1667

## Foglio3
Total
Story points | Estimated Time in hours | Actual Time in hours
10 | 35.75 | 41.25

## Foglio2
Tasks for all stories | Estimated Hours | Hours |  | E hours | E minutes | E conversion hours | hours | minutes | conversion hours
| 2h | 2h 15m |  | 2 | 0 | 2 | 2 | 15 | 2.25
| 6h | 11h 30m |  | 6 | 0 | 6 | 11 | 30 | 11.5
| 4h | 4h 30m |  | 4 | 0 | 4 | 4 | 30 | 4.5
| 15m | 10m |  | 0 | 15 | 0.25 | 0 | 10 | 0.16667
| 1h | 30m |  | 1 | 0 | 1 | 0 | 30 | 0.5
Hours to be added to each story
Tasks |  | E hours for each story | hours for each story
OQ-13 Create sql database |  | 0.4 | 0.45
OQ-25 Learning used technologies |  | 1.2 | 2.3
OQ-19 Add login/logout functionality |  | 0.8 | 0.9
OQ-14 Create and connect BitBucket repository |  | 0.05 | 0.033333
OQ-15 Populate Database |  | 0.2 | 0.1